## Sheet1
Sr. No. | Project Phases | Effort Estimate(Days) | Week | Planned Start Date | End Date | Resources
1 | Initiate Project
1.1 | Develop and analyze project charter
| (1) Define Scope | 1 | Week 1 | 2015-01-09 | 2015-01-10 | Entire Team
| (2) Define Requirements | 1 | Week 1 | 2015-01-10 | 2015-01-11 | Entire Team
| (3) Define Team-member roles | 0.25 | Week 1 | 2015-01-12 | 2015-01-12 | Entire Team
| (4) Identify high-level and low-level roles | 1 | Week 1 | 2015-01-12 | 2015-01-13 | Entire Team
| (5) Identify high-level budgets and control strategies | 1 | Week 1 | 2015-01-13 | 2015-01-14 | Entire Team
| (6) Hold review meeting | 0.5 | Week 1 | 2015-01-15 | 2015-01-15 | Entire Team
2 | Project Planning Phase
2.1 | Develop Project Plan
| (1) Develop work-breakdown structure | 1 | Week 2 | 2015-01-17 | 2015-01-18 | Entire Team
| (2) Develop project staffing plan | 1 | Week 2 | 2015-01-18 | 2015-01-19 | Entire Team
| (3) Develop project schedule | 1 | Week 2 | 2015-01-19 | 2015-01-20 | Entire Team
| (4) Define project milestones | 0.5 | Week 2 | 2015-01-20 | 2015-01-20 | Entire Team
| (5) Develop project budget | 1 | Week 2 | 2015-01-20 | 2015-01-21 | Entire Team
2.2 | Develop Project Control Plan
| (1) Develop communication plan | 0.5 | Week 2 | 2015-01-21 | 2015-01-21 | Entire Team
| (2) Develop quality management plan | 2 | Week 2 | 2015-01-22 | 2015-01-23 | Entire Team
2.3 | Finalize Project Plan
| (1) Hold review meeting | 0.25 | Week 2 | 2015-01-23 | 2015-01-23 | Entire Team
3 | Execute and Control Project
3.1 | Design Framework
| (1) Define framework stages and activities | 4 | Week 3 | 2015-01-24 | 2015-01-28 | Entire Team
| (2) Define functionalities to be incorporated | 2 | Week 3 | 2015-01-28 | 2015-01-30 | Entire Team
| (3) Define software tools to be used | 1 | Week 3 | 2015-01-30 | 2015-01-31 | Entire Team
3.2 | Build the Framework
| (1) Develop the framework | 20 | Week 4, 5, 6 | 2015-01-31 | 2015-02-20 | Entire Team
| (2) Review code for quality | 5 | Week 7 | 2015-02-20 | 2015-02-25 | Entire Team
| (3) Build application prototype | 10 | Week 8 | 2015-02-25 | 2015-03-05 | Entire Team
3.3 | Testing the application
| (1) Define test cases | 5 | Week 8, 9 | 2015-03-05 | 2015-03-10 | Entire Team
| (2) Test the usability of application | 2 | Week 9 | 2015-03-10 | 2015-03-12 | Entire Team
| (3) Adjust framework as per user feedback | 2 | Week 9 | 2015-03-12 | 2015-03-14 | Entire Team
3.4 | Risk Analysis
| (1) Define the Risk | 2 | Week 10 | 2015-03-14 | 2015-03-16 | Entire Team
| (2) Devise a Risk Management Plan | 2 | Week 10 | 2015-03-16 | 2015-03-18 | Entire Team
| (3) Make changes according to Plan | 2 | Week 10 | 2015-03-18 | 2015-03-20 | Entire Team
3.5 | Finalizing the Application
| (1) Make all changes according to result of stages | 3 | Week 11 | 2015-03-22 | 25/3/151 | Entire Team
| (2) Check for any errors or issues | 2 | Week 11 | 2015-03-25 | 2015-03-27 | Entire Team
| (3) Do a quality check | 2 | Week 11 | 2015-03-27 | 2015-03-29 | Entire Team
4 | Close Project
| (1) Conclude the project | 1 | Week 12 | 2015-03-30 | 2015-03-31 | Entire Team
| (2) Conduct a post project review | 0.5 | Week 12 | 2015-04-01 | 2015-04-01 | Entire Team